**August 2016 Referendum**

Submission of NDP to SDC - 11th January 2016

Checking submission & preparing publication – January 2016

Consultation – January to March 2016

Independent Examination – March to April 2016

Committee procedures starting approx 7th May 2016

Environment Committee June 2016

Electoral processes – Starting with Notice of Referendum 4th July 2016

Day of Poll - 11th August 2016

**February 2017 Referendum**

Submission of NDP to SDC - 20th June 2016

Checking submission & preparing publication – June 2016

Consultation – June to August 2016

Independent Examination – August to October 2016

Committee procedures starting approx 15th Oct 2016

Environment Committee December 2016

Electoral Services Team processes – Starting with Notice of Referendum 12th Jan 2017

Day of Poll - 16th February 2017